## Slide 1: Product Team Q3 Project Update
Presented by: Product Team | October 2026

## Slide 2: Quarter Overview
This quarter, the team completed three major initiatives: the membership system revamp, the mobile app v3.2 release, and the data dashboard launch, along with several minor improvements.
Overall, all projects are on track; the membership system revamp slipped approximately one week.
Details follow on the next slides.

## Slide 3: Project Status
Project | Planned | Actual | Status
Membership system revamp | Sep 15 | Sep 22 | Delayed approximately one week
Mobile app v3.2 | Aug 30 | Aug 30 | Completed
Data dashboard | Sep 30 | Sep 28 | Delivered two days early
Support ticket improvements | Sep 10 | Sep 10 | OK

## Slide 4: Membership System Revamp
The membership system revamp went live on Sep 22, approximately one week later than planned.
Following the revamp, the new-member sign-up conversion rate increased from 3.1% to 4.0%, a significant improvement.
The points rules were also adjusted, and existing members have raised no major concerns.
Next step: review the member tier logic to identify any edge cases.

## Slide 5: Mobile App v3.2 Release
Mobile app v3.2 shipped on time on Aug 30.
Post-release feedback has been largely positive, and the crash rate dropped to approximately 0.3%, a substantial improvement.
Weekly active users continued to grow (see chart).
Chart: Weekly active users (thousands)
| Jul | Aug | Sep
Weekly active users (thousands) | 124 | 131 | 146

## Slide 6: Issues We Ran Into
API integration took longer than expected, the test environment was unstable, and design revisions caused front-end rework — together these pushed the membership system about one week.
Going forward: agree on API specifications with the backend team earlier and involve the infra team on the test environment.
Going forward: move design reviews earlier, before development planning.

## Slide 7: Q4 Plan
Membership system phase 2: member tiers and a perks center, planned to launch at the end of November.
Mobile app v3.3: performance improvements and a notification center, planned to ship in mid-December.
Data dashboard: conversion analysis by channel, expected to go live in December.

## Slide 8: Where We Need Help
1) Test environment stability — support from the infra team would be appreciated
2) Schedule design reviews earlier, before development planning
3) Additional QA headcount for next quarter, as the team is currently short-staffed
Thank you.

## Slide 9: Summary and Next Steps
Q3: membership system revamp, mobile app v3.2 and the data dashboard all shipped; the membership revamp slipped about one week.
Next steps: review member tier logic; launch member tiers and perks center (end of November); ship app v3.3 (mid-December) and dashboard conversion analysis (December).
Where we need help: infra support for the test environment, earlier design reviews, and additional QA headcount for next quarter.